## Sheet1
I095-ACTUAL WEIGHT
Date: | 31.01.2026
Rev : | 1
|  | Contract |  | Actual |  |  | Chế tạo kiện
No. | Item | Weight-1 Unit (kg) | Weight-2 Unit (kg) | Weight-1 Unit (kg) | Weight-2 Unit (kg) | Remark |  |  | Manufacturing company
1 | Stack Template | 816.4746 | 1632.9493 | 846.7198 | 1693.4397 | IBS | IBS | Huấn | IBS
2 | Base Plate | 2268 | 4536 | 2268.9304 | 4537.8608 | IBS | IBS | Huấn | IBS
3 | Box #6 | 61482.8611 | 122965.7222 | 96328.229 | 192656.4581 | IBS | IBS | Sơn | IBS
4 | Box #5 | 65393.7196 | 130787.4392 | 65550.8518 | 131101.7036 | IBS | IBS | Tú | IBS
5 | Box #4 | 94675.7252 | 189351.4504 | 70509.1144 | 141018.2288 | IBS | IBS | Huấn | IBS
6 | Box #3 | 68563.8243 | 137127.6487 | 65260.0028 | 130520.0056 | TP | TP | Tùng | IBS
7 | Field Cross Beam (Top Beam-Box) | 29800 | 59600 | 35903.4751 | 71806.9502 | TP | L3 | LISEMCO 3 | IBS-LISEMCO 3
8 | DW - Inlet | 147107.1534 | 294214.3068 | 213447.55 | 426895.1 | TP | TP | Hưng | IBS
9 | DW - Outlet Duct | 32868.1184 | 65736.2367 | 27716.96 | 55433.92 | IBS | IBS | Trung | IBS
10 | SK - Stack & Breeching | 182480.7435 | 364961.4869 | 186695.01 | 373390.02 | TP | IBS | Lisemco 5 | IBS-LISEMCO 5
11 | Box #2 | 114976.04 | 229952.0799 | 114402.6779 | 228805.3557 | IBS | IBS | Huy | IBS
12 | Box #1 | 82933.2365 | 165866.473 | 82272.785 | 164545.5699 | TP | TP | Đồng | IBS
13 | CC - Basement Panel | 26786.8957 | 53573.7915 | 20796.1055 | 41592.211 | TP | L3 | LISEMCO 3 | IBS-LISEMCO 3
14 | CC - Attic Pane | 26316.452 | 52632.9041 | 24672.4357 | 49344.8714 | TP | L3 | LISEMCO 3 | IBS-LISEMCO 3
15 | CO+SCR Frame and Baffles | 40000 | 80000 | 30204.45 | 60408.9 | TP | PCC1 | A387 | IBS Chưa có vật tư | Dương Yêu cầu kho Chuẩn bị giao vật tư
16 | DW- CO/SCR | 144072.1091 | 288144.2182 | 139493.19 | 278986.38 | TP | TP | Hưng | IBS
17 | DW - Burner | 106465.9374 | 212931.8748 | 113091.5763 | 226183.1526 | TP | TP | Vemco | IBS
18 | PW - Stairtower | 16049.4771 | 32098.9542 | 88774.91 | 177549.82 | TP | PCC1 | PCC1 | PCC1
19 | PW - Spiral Stair | 20411.8661 | 40823.7322 | 20775.57 | 41551.14 | IBS | IBS | Lismeco 5 (Đã có văn bản xin trả lại IBS 07.03.2026) | IBS-LISEMCO 5
20 | PW - Platforms, Stairs, Ladders | 144135.3715 | 288270.743 | 128000 | 256000 |  | IBS
| LOT 1 | 18000 | 36000 |  |  | TP | DR | DRW | DRW
| LOT 2 | 34000 | 68000 |  |  | TP | IBS | Đồng | IBS
| LOT 3 | 34000 |  |  |  | IBS | IBS |  | IBS
| LOT 4 | 11000 |  |  |  | IBS | IBS |  | IBS
21 | Field installed top spool DUCT | 2866.7218 | 0 | 2866.7218 | 5733.4435 | TP | Tùng | Chuyển Tùng | Tùng
22 | BUMPER (Spec Rev 5 Ko sơn ) | 17894.3146 | 0 | 17894.3146 | 35788.6292 | TP | DR | DRW | DRW
23 | SHOP INSTALLED SIDE WALL GAS BYPASS BAFFLES DETAILS | 0 | 0 | 1816 | 3632 | IBS | IBS |  | IBS
24 | FIELD INSTALLED BASEMENT GAS BYPASS BAFFLES | 0 | 0 | 5707.8996 | 11415.7991 | TP | L3
25 | Pipe Rack | 0 | 0 | 40000 | 80000 | Chưa giao
26 | Pipe Support | 0 | 0 | 34000 | 68000 | Chưa giao
27 | DW - Transition Duct | 26717.0253 | 53434.0505 | 0 | 0 | N/A
28 | ER- ACOUSTIC SHROUD | 10807.5 | 21615 | 4704 | 9408 | TP | Thế Anh | TA |  | Dương Yêu cầu kho Chuẩn bị giao vật tư
| Total | 1552082.0671 | 2972642.0615 | 1633999.4796 | 3267998.9592
2

## BCTH-IBSHI-QLDA-095
BẢNG KẾ HOẠCH TỔNG THỂ TRIỂN KHAI THỰC HIỆN CÁC DỰ ÁN/ TABLE OF IMPLEMENTTAITON PLAN
Phòng, bộ phận báo cáo/ Department: ...
Kỳ (tháng) lập báo cáo/ Month No.: ...
Biểu mẫu số/Form No.: BCTH-IBSHI-QLDA-01
TABLE OF EXPECTED MANUFACTURING VOLUME ALLOCATION IN 2025 | [22 empty] | Cập nhật ngày/ Update to: | 2026.03.17
TỔNG NHÂN LỰC CẦN CHO CÁC DỰ ÁN (tính một tuần 6 ngày và ko tính thêm giờ) | STT/ No. | TÊN CÔNG TRÌNH, HẠNG MỤC, ĐẦU MỤC CÔNG VIỆC /PROJECT NAME, ITEM, DESCRIPTION | ĐVT/ UNIT | KHỐI LƯỢNG/ VOLUME | PHẠM VI THỰC HIỆN/ SCOPE OF WORKS |  | TIẾN ĐỘ THỰC HIỆN / SCHEDULE |  |  | PHẠM VI CÔNG VIỆC CHI TIẾT CỦA THẦU PHỤ/ SUB-CONTRACTOR'S SCOPE OF WORKS | [12 empty] | KHU VỰC THI CÔNG DỰ KIẾN/ EXPECTED FABRICATION AREA | GHI CHÚ/ REMARKS
[5 empty] | IBS HI | Sub-Contractor/ NAME | Bắt đầu/ Start | Kết thúc/ Finish | Shipping Frame | Cắt/ Cutting | GCCK/ Machining | Gá/ Fitup | Hàn/ Welding | Tổ hợp/ Try-assembly | Tháo dỡ/ Dismantle | Làm sạch/ Blasting | Sơn/ Painting | Bảo ôn/ Insulation | Chạy thử/ Commissioning | Chế tạo khung kiện | Đóng kiện/ Packing | Giao hàng/ Delivery
| (a) | (b) | (c) | (d) | (e) | (f) | (g) | (h) |  | (i-1) | (i-2) | (i-3) | (i-4) | (i-5) | (i-6) | (i-7) | (i-8) | (i-9) | (i-10) |  | (i-11) | (i-12) | (j) | (k)
D- | 1 | 25-VPI-I-095 |  | 3267998.9592
| A | UNIT 1 | kg | 1633999.4796
| 1 | Stack Template | kg | 846.7198 | IBS | Huấn | 2025-09-19 | 2025-10-30 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | N/A |  | IBS | IBS | IBS |  | DONE
| 2 | Base Plate | kg | 2268.9304 | IBS | Huấn | 2025-09-19 | 2025-10-30 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | N/A |  | IBS | IBS | IBS |  | DONE
| 3 | Box #6 | kg | 96328.229 | IBS | Sơn | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 4 | Box #5 | kg | 65550.8518 | IBS | Tú | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 5 | Box #4 | kg | 70509.1144 | IBS | Huấn | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 6 | Box #3 | kg | 65260.0028 | TP | Tùng | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | TP TÙNG | TP TÙNG |  |  | IBS | IBS | Giang Sơn |  | TP TÙNG | IBS | IBS
| 7 | Field Cross Beam (Top Beam-Box) | kg | 35903.4751 | TP | LISEMCO 3 | 2025-12-06 | 2026-01-15 | DONE | IBS | IBS | TP L3 | TP L3 |  |  | TP L3 | TP L3 | N/A |  | TP L3 | TP L3 | IBS
| 8 | DW - Inlet | kg | 213447.55 | TP | Hưng | 2025-11-02 | 2026-03-19 | Ongoing | IBS | IBS | TP HƯNG | TP HƯNG | TP HƯNG | TP HƯNG | IBS | IBS | Giang Sơn |  | TP HƯNG | IBS | IBS
| 9 | DW - Outlet Duct | kg | 27716.96 | IBS |  | 2025-12-10 | 2026-03-08 | DONE | IBS | IBS | IBS | IBS | IBS | IBS | IBS | IBS | N/A |  | IBS | IBS | IBS
| 10 | SK - Stack & Breeching | kg | 186695.01 | TP | Lisemco 5 | 2025-12-08 | 2026-03-20 | Ongoing | IBS | IBS | TPLISEMCO 5 | TP LISEMCO 5 | TP LISEMCO 5 | TP LISEMCO 5 | TP LISEMCO 5 | TP LISEMCO 5 | N/A |  | IBS | IBS | IBS |  | Dự kiến nhà máy chế tạo DẨ list để thứ tự ưu tiên
| 11 | Box #2 | kg | 114402.6779 | IBS | Huy | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | IBS | IBS |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 12 | Box #1 | kg | 82272.785 | TP | Đồng | 2025-11-08 | 2026-06-13 | DONE | IBS | IBS | TP ĐỒNG | TP ĐỒNG |  |  | IBS | IBS | Giang Sơn |  | TP ĐỒNG | IBS | IBS
| 13 | CC - Basement Panel | kg | 20796.1055 | TP | LISEMCO 3 | 2026-01-15 | 2026-03-19 | Ongoing | IBS | IBS | TP L3 | TP L3 |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 14 | CC - Attic Pane | kg | 24672.4357 | TP | LISEMCO 3 | 2026-01-15 | 2026-03-19 | Ongoing | IBS | IBS | TP L3 | TP L3 |  |  | IBS | IBS | Giang Sơn |  | IBS | IBS | IBS
| 15 | CO+SCR Frame and Baffles | kg | 30204.45 | TP | PCC1 | 2026-01-02 | 2026-03-20 | Ongoing | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | N/A | N/A |  | PCC1 | PCC1 | IBS
| 16 | DW- CO/SCR | kg | 139493.19 | TP | Hưng | 2026-01-02 | 2026-03-20 | Ongoing | IBS | IBS | TP HƯNG | TP HƯNG |  |  | IBS | IBS | Giang Sơn |  | Mr TÙNG | IBS | IBS
| 17 | DW - Burner | kg | 113091.5763 | TP | Vemco | 2025-12-25 | 2026-03-11 | Ongoing | IBS | IBS | TP LONG | TP LONG | TP LONG | TP LONG | IBS | IBS | Giang Sơn |  | TP LONG | IBS | IBS
| 18 | PW - Stairtower | m2 | 88774.91 | TP | PCC1 | 2026-01-10 | 2026-03-07 | DONE | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | PCC1 | N/A |  | PCC1 | PCC1 | IBS
E- | 19 | PW - Spiral Stair | kg | 20775.57 | IBS |  | 2026-01-20 | 2026-03-09 | Ongoing | IBS | IBS | IBS | IBS | IBS | IBS | IBS | IBS | N/A |  | IBS | IBS | IBS
F- | 20 | PW - Platforms, Stairs, Ladders | kg | 128000 | IBS |  | 2026-01-20 | 2026-03-25 | Ongoing
G- | 20.1 | LOT 1 | kg |  | TP | DRW | 2026-01-20 | 2026-03-25 | Ongoing | IBS | IBS | TP ĐR | TP ĐR | TP ĐR | TP ĐR | TP ĐR | TP ĐR | N/A |  | TP ĐR | TP ĐR | IBS
H- | 20.2 | LOT 2 | kg |  | TP | Đồng | 2026-01-20 | 2026-03-25 | Ongoing | IBS | IBS | TP ĐỒNG | TP ĐỒNG | TP ĐỒNG | TP ĐỒNG | IBS | IBS | N/A |  | TP ĐỒNG | IBS | IBS
| 20.3 | LOT 3 | kg |  | IBS |  | 2026-01-20 | 2026-03-25 | Ongoing | IBS | IBS | IBS | IBS | IBS | IBS | IBS | IBS | N/A |  | IBS | IBS | IBS
| 20.4 | LOT 4 | kg |  | IBS |  | 2026-01-20 | 2026-03-25 | Ongoing | IBS | IBS | IBS | IBS | IBS | IBS | IBS | IBS | N/A |  | IBS | IBS | IBS
| 25 | Field installed top spool DUCT | kg | 2866.7218 | TP | Tùng |  |  | Ongoing | IBS | IBS | TP TÙNG | TP TÙNG | IBS | IBS | IBS | IBS | N/A |  | TP TÙNG | IBS | IBS
| 26 | BUMPER (Spec Rev 5 Ko sơn ) | kg | 17894.3146 | TP | DRW |  |  | Ongoing | IBS | IBS | TP ĐR | TP ĐR | TP ĐR | TP ĐR | TP ĐR | N/A | N/A |  | TP ĐR | TP ĐR | IBS
| 27 | SHOP INSTALLED SIDE WALL GAS BYPASS BAFFLES DETAILS |  | 1816 | IBS |  |  |  |  | IBS | IBS | IBS | IBS |  |  | IBS | IBS | N/A |  | IBS | IBS | IBS
| 28 | FIELD INSTALLED BASEMENT GAS BYPASS BAFFLES | kg | 5707.8996 | TP | LISEMCO 3 |  |  |  | IBS | IBS | TP L3 | TP L3 |  |  | IBS | IBS | N/A |  | TP L3 | IBS | IBS
| 31 | ER- ACOUSTIC SHROUD | kg | 4704 | TP | Thế Anh |  |  |  | TA | TA | TA | TA |  |  | N/A | N/A | TP GIANG SƠN |  | IBS | IBS | IBS
| 29 | Pipe Rack | kg | 40000 | Chưa giao
| 30 | Pipe Support | kg | 34000 | Chưa giao
| 33 | ER:-Ínsulation |  |  | Chưa giao
| 34 | ER-Plate |  |  | Chưa giao
| 35 | ER-LINER |  |  | Chưa giao
| 36 | ER-Beam |  |  | Chưa giao
| 37 | ER - Fastener |  |  | Chưa giao
| B | UNIT 2 | kg | 1633999.4796
| 32 | Stack Template | kg | 846.7198 | IBS | Huấn
| 33 | Base Plate | kg | 2268.9304 | IBS | Huấn
| 34 | Box #6 | kg | 96328.229 | IBS | Sơn
| 35 | Box #5 | kg | 65550.8518 | IBS | Tú
| 36 | Box #4 | kg | 70509.1144 | IBS | Huấn
| 37 | Box #3 | kg | 65260.0028 | TP | Tùng
| 38 | Field Cross Beam (Top Beam-Box) | kg | 35903.4751 | TP | LISEMCO 3
| 39 | DW - Inlet | kg | 213447.55 | TP | Hưng
| 40 | DW - Outlet Duct | kg | 27716.96 | IBS | Lisemco 5
| 41 | SK - Stack & Breeching | kg | 186695.01 | IBS | Lisemco 5
| 42 | Box #2 | kg | 114402.6779 | IBS | Huy
| 43 | Box #1 | kg | 82272.785 | TP | Đồng
| 44 | CC - Basement Panel | kg | 20796.1055 | TP | LISEMCO 3
| 45 | CC - Attic Pane | kg | 24672.4357 | TP | LISEMCO 3
| 46 | CO+SCR Frame and Baffles | kg | 30204.45 | TP | PCC1
| 47 | DW- CO/SCR | kg | 139493.19 | TP | Hưng
| 48 | DW - Burner | kg | 113091.5763 | TP | Vemco
| 49 | PW - Stairtower | m2 | 88774.91 | TP | PCC1
| 50 | PW - Spiral Stair | kg | 20775.57 | IBS | IBS-Lisemco 5
| 51 | PW - Platforms, Stairs, Ladders | kg | 128000 | IBS
| 52 | LOT 1 | kg |  | TP | DRW
| 53 | LOT 2 | kg |  | TP | Đồng
| 54 | LOT 3 | kg |  | IBS
| 55 | LOT 4 | kg |  | IBS
| 56 | Field installed top spool DUCT | kg | 2866.7218 | TP | Chuyển Tùng
| 57 | BUMPER (Spec Rev 5 Ko sơn ) | kg | 17894.3146 | TP | DRW
| 58 | SHOP INSTALLED SIDE WALL GAS BYPASS BAFFLES DETAILS |  | 1816 | IBS
| 59 | FIELD INSTALLED BASEMENT GAS BYPASS BAFFLES | kg | 5707.8996 | TP | LISEMCO 3
| 60 | Pipe Rack | kg | 40000 | Chưa giao
| 61 | Pipe Support | kg | 34000 | Chưa giao
| 62 | DW - Transition Duct | kg | 0 | N/A
| 63 | ER- ACOUSTIC SHROUD | kg | 4704 | TP | Thế Anh
Ghi chú/ Note:
- Phần cắt (cutting): bao gồm cả phần vát mép và mài./Cutting: includes both beveling and grinding.
- Phần hàn: gá đính: bao gồm cả phần sửa sắt hàn sau khi làm sạch sơ bộ./Tack welding: Including repairing after Sweep blasting
Quy định, Cách thức điền thông tin: Regulations, How to fill in information:
- Biều này được lập ngay sau khi hợp đồng mới được ký kết và được cập nhật khi các bước sau được triển khai: (i) tiến độ lập, đệ trình khách; (ii) thay đổi phạm vi công việc; (iii) cập nhật hàng tháng theo kế hoạch tháng của công ty/This form shall be made immediately after the new contract is signed and updated when the following steps are implemented: (i) the project schedule is made and submitted to the client; (ii) changes in the scope of work; (iii) monthly updates according to the company's monthly plan.
- Các nội dung tô màu đỏ chỉ là ví dụ và người/ bộ phận lập báo cáo phải tự điều chỉnh lại nội dung theo kế hoạch lập cho phù hợp/ The contents in red are only examples and the reporting person/department must adjust the content according to the plan accordingly.
- Cột (b) điền ít nhất các trường thông tin chính: (i) Tên dự án -- (ii) Tên Cụm thiết bị -- (iii)Tên thiết bị/ chi tiết. Xem xét phân bổ nhỏ hơn tương ứng với phần việc giao thầu phụ, nhà máy thực hiện để khớp thông tin với các cột e, f và I mục tiêu càng chi tiết càng tốt và được nhóm (group) theo các cụm tương ứng dễ kiểm tra, theo dõi./Column (b) fill in at least the main information fields: (i) Project name -- (ii) Equipment Cluster name -- (iii) Equipment name/details. Considering the smaller allocation corresponding to the subcontracting part, the factory performs to match the information with the target columns e, f and I in as much detail as possible and is grouped in corresponding clusters that are easy to check and track.
- Cột e, f,i: là các cột lựa chọn, thuộc phạm vi thực hiện bên nào thì đánh ký tự "x"./ Columns e, f, i: are the selecting columns, in the scope of implementation, the character "x" is typed.
- Cột g, h: Tiến độ cấp 2 cho cụn chi tiết và cấp 3 cho phần chi tiết./Columns g, h: Progress level 2 for detailed segments and level 3 for detailed sections
- Cột f: Khu vực thi công ghi rõ các trường: (i) Trong/ Ngoài nhà máy; (ii) trong nhà máy: Trong xưởng/ ngoài mặt bằng tổ hợp và cụ thể xưởng/ khu vực nào theo quy định tổng mặt bằng./Column f: The construction area clearly states the following fields: (i) Inside / Outside the factory; (ii) In the factory: In the workshop/outside the complex premises and specifically the workshop/area according to the regulations on the total area plan.
- Cột k: Các nội dung khác yêu cầu chưa thể hiện hết trong các cột phía trước./ Column k: Other required contents are not fully reflected in the previous columns..
|  |  | ĐƠN VỊ BÁO CÁO/ REPORT BY |  |  |  | GIÁM ĐỐC PHỤ TRÁCH/ DIRECTOR IN CHARGE
|  | Người lập/Prepared by |  | Phê duyệt/ Approved by
Note on U26: Admin: Mr Tùng nhận làm hỗ trợ Mr Hung 28.03.26