## lenh_san_xuat
LỆNH SẢN XUẤT
⚠ Cột nền XANH = bắt buộc ¦ Cột nền VÀNG = tuỳ chọn ¦ Dòng 3 ẩn = tên cột DB (không sửa)
lenh_sx_code | project_code | job_code | sub_item | noi_dung | team_code | don_vi_tinh | kl_phan_giao | don_gia | ngay_bat_dau | ngay_ket_thuc | trang_thai
Mã lệnh SX | Mã dự án | Mã công việc | Phân loại phụ | Nội dung | Mã tổ SX | ĐVT | KL phân giao | Đơn giá khoán | Ngày bắt đầu | Ngày kết thúc | Trạng thái
LSX-25-BRA-I-082-001 | 25-BRA-I-082 | TT | TT | Pha cắt tôn tấm | TO-PC2 | kg | 7800 |  | 2025-03-01 | 2025-04-30 | issued
LSX-25-BRA-I-082-002 | 25-BRA-I-082 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 2800 |  | 2025-03-01 | 2025-04-30 | issued
LSX-25-BRA-I-082-003 | 25-BRA-I-082 | IN | IN | Pha cắt Inox, hợp kim | TO-PC2 | kg |  |  |  |  | issued
LSX-25-BRA-I-082-004 | 25-BRA-I-082 | SL | SL | Gia công sấn, lốc | TO-GCCK | kg | 10600 |  | 2025-03-01 | 2025-04-30 | issued
LSX-25-BRA-I-082-005 | 25-BRA-I-082 | KC/TB/CT/TĐ | TB | Chế tạo Damper | TO-GL2 | kg | 10600 |  | 2025-03-16 | 2025-06-30 | issued
LSX-25-BRA-I-082-006 | 25-BRA-I-082 | KC/TB/CT/TĐ | TB | Chế tạo Damper | TO-HAN1 | kg | 10600 |  | 2025-03-16 | 2025-06-30 | issued
LSX-25-BRA-I-082-007 | 25-BRA-I-082 | CT | kc | Chế tạo sàn biện pháp | TO-GL2 | bộ | 2 |  | 2025-03-16 | 2025-06-30 | issued
LSX-25-BRA-I-082-008 | 25-BRA-I-082 | KK | KC | Khung kiện | TO-GL2 | bộ | 2 |  | 2025-10-20 | 2025-10-30 | issued
LSX-25-BRA-I-082-009 | 25-BRA-I-082 | KK | KC | Khung kiện | TO-HAN1 | bộ | 2 |  | 2025-10-20 | 2025-10-30 | issued
LSX-25-BRA-I-082-010 | 25-BRA-I-082 | LĐ | LĐ | Tổ hợp sản phẩm (sau sơn, hoặc sau bảo ôn) | TO-GL2 | bộ | 2 |  | 2025-09-01 | 2025-10-01 | issued
LSX-25-BRA-I-082-011 | 25-BRA-I-082 | CN | CN | Chạy thử chức năng | TO-GL2 | bộ | 2 |  | 2025-10-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-012 | 25-BRA-I-082 | LS+S - TB/BL | LS+S - TB | Làm sạch | TO-SON | m2 | 300 |  | 2025-06-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-013 | 25-BRA-I-082 | LS+S - TB/BL | LS+S - TB | Sơn sản phẩm lớp 1 | TO-SON | m2 | 300 |  | 2025-06-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-014 | 25-BRA-I-082 | LS+S - TB/BL | LS+S - TB | Sơn sản phẩm lớp 2 | TO-SON | m2 | 300 |  | 2025-06-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-015 | 25-BRA-I-082 | LS+S - IN | LS+S - IN | Làm sạch, Sơn sản phẩm vật liệu hợp kim (ghi rõ số lớp sơn) | TO-SON | m2 | 50 |  | 2025-06-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-016 | 25-BRA-I-082 | LS+S - KK | LS+S - KK | Làm sạch, Sơn khung kiện (ghi rõ số lớp sơn) | TO-SON | m2 | 25 |  | 2025-06-01 | 2025-10-31 | issued
LSX-25-BRA-I-082-017 | 25-BRA-I-082 | DK1 | DK1 | Dạng Khung kiện | TO-TH | kg | 13000 |  | 2025-10-28 | 2025-10-31 | issued
LSX-25-BRA-I-082-018 | 25-BRA-I-082 | CO | CO | Giao hàng Container (cho hàng vào container, lashing) | TO-TH | kg | 13000 |  |  |  | issued
LSX-25-IBS-O-086-019 | 25-IBS-O-086 | LS+S - TB/BL | TB | Làm sạch, Sơn sản phẩm (chỉ làm sạch ) | TO-SON | Chiếc | 21 |  | 2025-08-06 |  | issued
LSX-25-VPI-I-095-020 | 25-VPI-I-095 | TT | TT | Pha cắt tôn tấm | TO-PC2 | kg | 1003915.7969 |  | 2025-10-01 | 2026-01-30 | issued
LSX-25-VPI-I-095-021 | 25-VPI-I-095 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 1227008.1962 |  | 2025-10-01 | 2026-01-30 | issued
LSX-25-VPI-I-095-022 | 25-VPI-I-095 | IN | IN | Pha cắt Inox, hợp kim | TO-PC2 | kg | 265271.1996 |  | 2025-10-01 | 2026-01-30 | issued
LSX-25-VPI-I-095-023 | 25-VPI-I-095 | TT | TT | Pha cắt tôn tấm | TO-PC2 | kg | 1003915.7969 |  | 2026-02-01 | 2026-04-30 | issued
LSX-25-VPI-I-095-024 | 25-VPI-I-095 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 1227008.1962 |  | 2026-02-01 | 2026-04-30 | issued
LSX-25-VPI-I-095-025 | 25-VPI-I-095 | IN | IN | Pha cắt Inox, hợp kim | TO-PC2 | kg | 265271.1996 |  | 2026-02-01 | 2026-04-30 | issued
LSX-25-VPI-I-095-026 | 25-VPI-I-095 | GC |  | Gia công |  | kg | 2496195.1927 |  |  |  | pending
LSX-25-VPI-I-095-027 | 25-VPI-I-095 | SL | GC | Gia công sấn, lốc, khoan lỗ, doa lỗ, vệ sinh GCCK trước giao hàng | TO-GCCK | kg | 2496195.1927 |  | 2025-10-01 | 2026-01-30 | issued
LSX-25-VPI-I-095-028 | 25-VPI-I-095 | SL | GC | Gia công sấn, lốc, khoan lỗ, doa lỗ, vệ sinh GCCK trước giao hàng | TO-GCCK | kg | 2496195.1927 |  | 2026-02-01 | 2026-04-30 | issued
LSX-25-VPI-I-095-029 | 25-VPI-I-095 | G+H |  | Tạm chia do bản vẽ nên không rõ đầu mục |  | kg | 974556.3735 |  |  |  | pending
LSX-25-VPI-I-095-030 | 25-VPI-I-095 | PC | KC | Tổ hợp thành dầm H (Hàn DW1.8, NDT theo bản vẽ) | TP | kg | 45838.08 |  | 2025-10-01 | 2025-11-30 | subcontract
LSX-25-VPI-I-095-031 | 25-VPI-I-095 | PC | KC | Base plate | TO-GL3 | kg | 4536 |  | 2025-10-01 | 2025-10-30 | issued
LSX-25-VPI-I-095-032 | 25-VPI-I-095 | PC | KC | INLET DUCT (hàn râu bảo ôn) | TP | kg | 160593.64 |  | 2025-10-15 | 2026-01-30 | subcontract
LSX-25-VPI-I-095-033 | 25-VPI-I-095 | PC | KC | BURNER DUCT (hàn râu bảo ôn) | TP | kg | 77533.8363 |  | 2025-12-19 | 2026-01-30 | subcontract
LSX-25-VPI-I-095-034 | 25-VPI-I-095 | PC | KC | OUTLET DUCT (hàn râu bảo ôn) | TO-GL1 | kg | 27604.86 |  | 2025-12-05 | 2026-01-30 | issued
LSX-25-VPI-I-095-035 | 25-VPI-I-095 | PC | KC | Box #1 | TP | kg | 73316.5462 |  | 2025-12-05 | 2026-02-14 | subcontract
LSX-25-VPI-I-095-036 | 25-VPI-I-095 | PC | KC | Box #2 | TO-GL4 | kg | 95554.4503 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-037 | 25-VPI-I-095 | PC | KC | Box #3 | TP | kg | 58840.8602 |  | 2025-12-05 | 2026-02-14 | subcontract
LSX-25-VPI-I-095-038 | 25-VPI-I-095 | PC | KC | Box #4 | TO-GL3 | kg | 64106.16 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-039 | 25-VPI-I-095 | PC | KC | Box #5 | TO-GL5 | kg | 61021.0195 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-040 | 25-VPI-I-095 | PC | KC | Box #6 | TO-GL2 | kg | 91484.4391 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-041 | 25-VPI-I-095 | PC | KC | Stack Templates | TO-GL3 | kg | 1632.9493 |  | 2025-10-01 | 2025-10-30 | issued
LSX-25-VPI-I-095-042 | 25-VPI-I-095 | PC | KC | DW- CO/SCR | TP | kg | 120536.8063 |  | 2025-12-25 | 2025-03-04 | subcontract
LSX-25-VPI-I-095-043 | 25-VPI-I-095 | PC | KC | DW- CO/SCR |  | kg | 120536.8063 |  |  |  | pending
LSX-25-VPI-I-095-044 | 25-VPI-I-095 | PC | KC | DW- CO/SCR (LINER) |  | kg | 17258 |  |  |  | pending
LSX-25-VPI-I-095-045 | 25-VPI-I-095 | PC | KC | Tổ hợp thành dầm H (Hàn DW1.8, NDT theo bản vẽ) | TP | kg | 45838.08 |  | 2025-10-01 | 2025-11-30 | subcontract
LSX-25-VPI-I-095-046 | 25-VPI-I-095 | PC | KC | Base plate | TO-HAN1 | kg | 4536 |  | 2025-10-01 | 2025-10-30 | issued
LSX-25-VPI-I-095-047 | 25-VPI-I-095 | PC | KC | INLET DUCT (hàn râu bảo ôn) | TP | kg | 160593.64 |  | 2025-10-15 | 2026-01-30 | subcontract
LSX-25-VPI-I-095-048 | 25-VPI-I-095 | PC | KC | BURNER DUCT (hàn râu bảo ôn) | TP | kg | 77533.8363 |  | 2025-12-19 | 2026-01-30 | subcontract
LSX-25-VPI-I-095-049 | 25-VPI-I-095 | PC | KC | OUTLET DUCT (hàn râu bảo ôn) | TO-HAN2 | kg | 27604.86 |  | 2025-12-05 | 2026-01-30 | issued
LSX-25-VPI-I-095-050 | 25-VPI-I-095 | PC | KC | Box #1 | TP | kg | 73316.5462 |  | 2025-12-05 | 2026-02-14 | subcontract
LSX-25-VPI-I-095-051 | 25-VPI-I-095 | PC | KC | Box #2 | TO-HAN2 | kg | 95554.4503 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-052 | 25-VPI-I-095 | PC | KC | Box #3 | TP | kg | 58840.8602 |  | 2025-12-05 | 2026-02-14 | subcontract
LSX-25-VPI-I-095-053 | 25-VPI-I-095 | PC | KC | Box #4 | TO-HAN1 | kg | 64106.16 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-054 | 25-VPI-I-095 | PC | KC | Box #5 | TO-HAN1 | kg | 61021.0195 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-055 | 25-VPI-I-095 | PC | KC | Box #6 | TO-HAN1 | kg | 91484.4391 |  | 2025-12-05 | 2026-02-28 | issued
LSX-25-VPI-I-095-056 | 25-VPI-I-095 | PC | KC | Stack Templates | TO-HAN1 | kg | 1632.9493 |  | 2025-10-01 | 2025-10-30 | issued
LSX-25-VPI-I-095-057 | 25-VPI-I-095 | PC | KC | DW- CO/SCR | TP | kg | 120536.8063 |  | 2025-12-25 | 2026-02-12 | subcontract
LSX-25-VPI-I-095-058 | 25-VPI-I-095 | PC | KC | DW- CO/SCR |  | kg | 120536.8063 |  |  |  | pending
LSX-25-VPI-I-095-059 | 25-VPI-I-095 | PC | KC | DW- CO/SCR (LINER) |  | kg | 17258 |  |  |  | pending
LSX-25-VPI-I-095-060 | 25-VPI-I-095 | PC | KC | INLET DUCT (hàn râu bảo ôn) | TP | kg | 160593.64 |  | 2026-01-20 | 2026-02-14 | subcontract
LSX-25-VPI-I-095-061 | 25-VPI-I-095 | PC | KC | BURNER DUCT (hàn râu bảo ôn) | TP | kg | 77533.8363 |  | 2026-01-30 | 2/30/2026 | subcontract
LSX-25-VPI-I-095-062 | 25-VPI-I-095 | PC | KC | OUTLET DUCT (hàn râu bảo ôn) | TO-GL1 | kg | 27604.86 |  | 2026-01-26 | 2026-02-10 | issued
LSX-25-VPI-I-095-063 | 25-VPI-I-095 | PC | KC | DW- CO/SCR | TP | kg | 120536.8063 |  | 2026-02-12 | 26/2/2026 | subcontract
LSX-25-WNC-I-097-064 | 25-WNC-I-097 | PC1 | TT | Pha cắt tôn tấm hạng mục 1617 | TO-PC2 | kg | 4895 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-065 | 25-WNC-I-097 | PC2 | TH | Pha cắt thép hình hạng mục 1617 | TO-PC3 | kg | 3319 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-066 | 25-WNC-I-097 | PC3 | TT | Pha cắt tôn tấm hạng mục 1627 | TO-PC2 | kg | 3932 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-067 | 25-WNC-I-097 | PC4 | TH | Pha cắt thép hình hạng mục 1627 | TO-PC3 | kg | 26805 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-068 | 25-WNC-I-097 | PC5 | TT | Pha cắt tôn tấm hạng mục 1634 | TO-PC2 | kg | 50332 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-069 | 25-WNC-I-097 | PC6 | TH | Pha cắt thép hình hạng mục 1634 | TO-PC3 | kg | 63517 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-070 | 25-WNC-I-097 | PC7 | TT | Pha cắt tôn tấm hạng mục 1645 | TO-PC2 | kg | 2139 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-071 | 25-WNC-I-097 | PC8 | TH | Pha cắt thép hình hạng mục 1645 | TO-PC3 | kg | 2443 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-072 | 25-WNC-I-097 | PC9 | TT | Pha cắt tôn tấm hạng mục 1652 | TO-PC2 | kg | 1686 |  | 2025-08-01 | 2026-02-10 | issued
LSX-25-WNC-I-097-073 | 25-WNC-I-097 | PC10 | TH | Pha cắt thép hình hạng mục 1652 | TO-PC3 | kg | 6535 |  | 2025-08-01 | 2026-02-10 | issued
LSX-25-WNC-I-097-074 | 25-WNC-I-097 | PC11 | TT | Pha Cắt tôn tấm khung kiện | TO-PC2 | kg | 1526.565 |  | 2025-10-10 | 2026-08-30 | issued
LSX-25-WNC-I-097-075 | 25-WNC-I-097 | PC12 | TH | Pha Cắt thép hình khung kiện | TO-PC3 | kg | 20667.0667 |  | 2025-10-10 | 2026-08-30 | issued
LSX-25-WNC-I-097-076 | 25-WNC-I-097 | GC1 | SL | Gia công sấn, lốc hạng mục MLI 1617 | TO-GCCK | kg | 8460 |  | 2025-08-01 | 2026-02-10 | issued
LSX-25-WNC-I-097-077 | 25-WNC-I-097 | GC2 | SL | Gia công sấn, lốc hạng mục MLI 1634 | TO-GCCK | kg | 112695 |  | 2025-10-10 | 2026-08-30 | issued
LSX-25-WNC-I-097-078 | 25-WNC-I-097 | GC3 | KH | Khoan lỗ hạng mục MLI 1617 | TO-GCCK | kg | 8214 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-079 | 25-WNC-I-097 | GC4 | KH | Khoan lỗ hạng mục MLI 1627 | TO-GCCK | kg | 30425 |  | 2025-08-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-080 | 25-WNC-I-097 | GC5 | KH | Khoan lỗ hạng mục MLI 1634 | TO-GCCK | kg | 112695 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-081 | 25-WNC-I-097 | GC6 | KH | Khoan lỗ hạng mục MLI 1645 | TO-GCCK | kg | 5835 |  | 2025-08-01 | 2026-05-30 | issued
LSX-25-WNC-I-097-082 | 25-WNC-I-097 | GC7 | CK | Gia công chính xác (tiện, phay, bào, ...) | TO-GCCK | kg |  |  |  |  | issued
LSX-25-WNC-I-097-083 | 25-WNC-I-097 | CT1 | TB | Đính gá Steel frame Unit 3 (MLI-1617) | TO-GL2 | kg | 1009 |  | 2025-12-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-084 | 25-WNC-I-097 | CT2 | TB | Đính gá panels (outer sheet 4mm and stiffeners), outer sheet welded through Unit 3 (MLI-1617) | TO-GL2 | kg | 198 |  | 2025-12-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-085 | 25-WNC-I-097 | CT3 | TB | Đính gá Steel construction Walkway/Duct Unit 3 (MLI-1617) | TO-GL2 | kg | 98 |  | 2025-12-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-086 | 25-WNC-I-097 | CT4 | TB | Đính gá Handrail & Ladder Walkway Unit 3 (MLI-1617) | TO-GL2 | kg | 114 |  | 2025-12-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-087 | 25-WNC-I-097 | CT5 | TB | Đính gá Flashing Kit; painted (S.N 8.2) Unit 3 (MLI-1617) | TO-GL2 | kg | 273 |  | 2025-12-01 | 2026-02-26 | issued
LSX-25-WNC-I-097-088 | 25-WNC-I-097 | CT6 | TB | Đính gá Steel frame Unit 4, Unit 5 (MLI-1617) | TO-GL5 | kg | 2018 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-089 | 25-WNC-I-097 | CT7 | TB | Đính gá panels (outer sheet 4mm and stiffeners), outer sheet welded through Unit 4, Unit 5 (MLI-161 | TO-GL5 | kg | 396 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-090 | 25-WNC-I-097 | CT8 | TB | Đính gá Steel construction Walkway/Duct Unit 4, Unit 5 (MLI-1617) | TO-GL5 | kg | 196 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-091 | 25-WNC-I-097 | CT9 | TB | Đính gá Handrail & Ladder Walkway Unit 4, Unit 5 (MLI-1617) | TO-GL5 | kg | 228 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-092 | 25-WNC-I-097 | CT10 | TB | Đính gá Flashing Kit; painted (S.N 8.2) Unit 4, Unit 5 (MLI-1617) | TO-GL5 | kg | 546 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-093 | 25-WNC-I-097 | CT11 | TB | Hàn Steel frame Unit 3, Unit 4, Unit 5 (MLI-1617) | TO-HAN1 | kg | 3027 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-094 | 25-WNC-I-097 | CT12 | TB | Hàn panels (outer sheet 4mm and stiffeners), outer sheet welded through Unit 3, Unit 4, Unit 5 (MLI | TO-HAN1 | kg | 594 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-095 | 25-WNC-I-097 | CT13 | TB | Hàn Steel construction Walkway/Duct Unit 3, Unit 4, Unit 5 (MLI-1617) | TO-HAN1 | kg | 294 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-096 | 25-WNC-I-097 | CT14 | TB | Hàn Handrail & Ladder Walkway Unit 3, Unit 4, Unit 5 (MLI-1617) | TO-HAN1 | kg | 342 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-097 | 25-WNC-I-097 | CT15 | TB | Hàn Flashing Kit; painted (S.N 8.2) Unit 3, Unit 4, Unit 5 (MLI-1617) | TO-HAN1 | kg | 819 |  | 2026-01-02 | 2026-04-29 | issued
LSX-25-WNC-I-097-098 | 25-WNC-I-097 | CT16 | TB | Đính gá KCT Unit 3 (MLI-1627) | TO-GL5 | kg | 5629 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-099 | 25-WNC-I-097 | CT17 | TB | Đính gá Kết cấu sàn, duct Unit 3 (MLI-1627) | TO-GL5 | kg | 169 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-100 | 25-WNC-I-097 | CT18 | TB | Đính gá Kết cấu lan can, cầu thang Unit 3 (MLI-1627) | TO-GL5 | kg | 287 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-101 | 25-WNC-I-097 | CT19 | TB | Hàn KCT Unit 3 (MLI-1627) | TO-HAN1 | kg | 5629 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-102 | 25-WNC-I-097 | CT20 | TB | Hàn Kết cấu sàn, duct Unit 3 (MLI-1627) | TO-HAN1 | kg | 169 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-103 | 25-WNC-I-097 | CT21 | TB | Hàn Kết cấu lan can, cầu thang Unit 3 (MLI-1627) | TO-HAN1 | kg | 287 |  | 2025-12-01 | 2026-01-26 | issued
LSX-25-WNC-I-097-104 | 25-WNC-I-097 | CT22 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL3 | kg | 3396.38 |  | 2025-11-18 | 2025-12-28 | issued
LSX-25-WNC-I-097-105 | 25-WNC-I-097 | CT23 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL4 | kg | 475.484 |  | 2025-11-18 | 2025-12-28 | issued
LSX-25-WNC-I-097-106 | 25-WNC-I-097 | CT24 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL5 | kg | 4162.69 |  | 2025-11-18 | 2025-12-28 | issued
LSX-25-WNC-I-097-107 | 25-WNC-I-097 | CT25 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN1 | kg | 7559 |  | 2025-11-18 | 2025-12-28 | issued
LSX-25-WNC-I-097-108 | 25-WNC-I-097 | CT26 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN2 | kg | 475.484 |  | 2025-11-18 | 2025-12-28 | issued
LSX-25-WNC-I-097-109 | 25-WNC-I-097 | CT27 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL1 | kg | 7587.5926 |  | 2026-01-05 | 2026-02-25 | issued
LSX-25-WNC-I-097-110 | 25-WNC-I-097 | CT28 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL3 | kg | 8396.6264 |  | 2026-01-05 | 2026-02-25 | issued
LSX-25-WNC-I-097-111 | 25-WNC-I-097 | CT29 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL4 | kg | 6133.9093 |  | 2026-01-05 | 2026-02-28 | issued
LSX-25-WNC-I-097-112 | 25-WNC-I-097 | CT30 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN1 | kg | 8396.6264 |  | 2026-01-05 | 2026-02-28 | issued
LSX-25-WNC-I-097-113 | 25-WNC-I-097 | CT31 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN2 | kg | 13722 |  | 2026-01-05 | 2026-02-25 | issued
LSX-25-WNC-I-097-114 | 25-WNC-I-097 | CT32 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL1 | kg | 7587.5926 |  | 2026-02-26 | 2026-03-28 | issued
LSX-25-WNC-I-097-115 | 25-WNC-I-097 | CT33 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL3 | kg | 8396.6264 |  | 2026-02-26 | 2026-03-28 | issued
LSX-25-WNC-I-097-116 | 25-WNC-I-097 | CT34 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL4 | kg | 6133.9093 |  | 2026-02-26 | 2026-03-28 | issued
LSX-25-WNC-I-097-117 | 25-WNC-I-097 | CT35 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN1 | kg | 8396.6264 |  | 2026-02-26 | 2026-03-28 | issued
LSX-25-WNC-I-097-118 | 25-WNC-I-097 | CT36 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN2 | kg | 13722 |  | 2026-02-26 | 2026-03-28 | issued
LSX-25-WNC-I-097-119 | 25-WNC-I-097 | CT37 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL1 | kg | 7587.5926 |  | 2026-03-28 | 2026-05-15 | issued
LSX-25-WNC-I-097-120 | 25-WNC-I-097 | CT38 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL3 | kg | 8396.6264 |  | 2026-03-28 | 2026-05-15 | issued
LSX-25-WNC-I-097-121 | 25-WNC-I-097 | CT39 | TB | Đính gá Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1. | TO-GL4 | kg | 6133.9093 |  | 2026-03-28 | 2026-05-15 | issued
LSX-25-WNC-I-097-122 | 25-WNC-I-097 | CT40 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN1 | kg | 8396.6264 |  | 2026-03-28 | 2026-05-15 | issued
LSX-25-WNC-I-097-123 | 25-WNC-I-097 | CT41 | TB | Hàn Steel frame, Panel (outer sheet 4mm and stiffeners) acc. to drawings; HDG or painted (S.N 1.2, S | TO-HAN2 | kg | 13722 |  | 2026-03-28 | 2026-05-15 | issued
LSX-25-WNC-I-097-124 | 25-WNC-I-097 | CT42 | TB | Gá lắp Kết cấu thép Unit 3(MLI-1652) | TO-PC3 | kg | 1466 |  | 2025-12-01 | 2025-12-25 | issued
LSX-25-WNC-I-097-125 | 25-WNC-I-097 | CT43 | TB | Hàn Kết cấu thép Unit 3(MLI-1652) | TO-HAN1 | kg | 1466 |  | 2025-12-01 | 2025-12-25 | issued
LSX-25-WNC-I-097-126 | 25-WNC-I-097 | CT44 | KK | Đính gá Khung kiện (Shipment #1, #2) theo Rev 00 | TO-PC3 | kg | 1002.32 |  | 2025-10-01 | 2025-11-01 | issued
LSX-25-WNC-I-097-127 | 25-WNC-I-097 | CT45 | KK | Đính gá Khung kiện (Shipment #1, #2) theo Rev 01 | TO-PC3 | kg | 2860.5408 |  | 2025-11-01 | 2025-12-01 | issued
LSX-25-WNC-I-097-128 | 25-WNC-I-097 | CT46 | KK | Hàn Khung kiện (Shipment #1, #2) theo Rev 01 | TO-HAN1 | kg | 2860.5408 |  | 2025-11-01 | 2025-12-01 | issued
LSX-25-WNC-I-097-129 | 25-WNC-I-097 | CT47 | KK | Đính gá Khung kiện (Shipment #3) | TO-PC3 | kg | 4119 |  | 2026-01-03 | 2026-02-03 | issued
LSX-25-WNC-I-097-130 | 25-WNC-I-097 | CT48 | KK | Hàn Khung kiện (Shipment #3) | TO-HAN2 | kg | 4119 |  | 2026-01-03 | 2026-02-03 | issued
LSX-25-WNC-I-097-131 | 25-WNC-I-097 | CT49 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 1 | TO-GL3 | kg | 22456 |  | 2025-12-28 | 2026-01-12 | issued
LSX-25-WNC-I-097-132 | 25-WNC-I-097 | CT50 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 2 | TO-GL3 | kg | 22456 |  | 2026-02-25 | 2026-03-10 | issued
LSX-25-WNC-I-097-133 | 25-WNC-I-097 | CT51 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 3 | TO-GL3 | kg | 22456 |  | 2026-03-28 | 2026-04-10 | issued
LSX-25-WNC-I-097-134 | 25-WNC-I-097 | CT52 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 4 | TO-GL3 | kg | 22456 |  | 2026-05-16 | 2026-05-29 | issued
LSX-25-WNC-I-097-135 | 25-WNC-I-097 | CT53 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 5 | TO-GL3 | kg | 22456 |  | 2026-05-01 | 2026-05-14 | issued
LSX-25-WNC-I-097-136 | 25-WNC-I-097 | CT54 | TB | Tổ hợp sản phẩm (MLI-1645) Unit 1 | TO-GL3 | kg | 1468.3534 |  | 2025-12-28 | 2026-01-12 | issued
LSX-25-WNC-I-097-137 | 25-WNC-I-097 | SO1 | TB | Làm sạch, Sơn sản phẩm (làm sạch SA2.5 sơn lớp 1) | TO-SON | m2 | 5658.6 |  | 2025-10-10 | 2026-08-15 | issued
LSX-25-WNC-I-097-138 | 25-WNC-I-097 | SO2 | TB | Sơn sản phẩm: Lớp 2 | TO-SON | m2 | 7270.3447 |  | 2025-10-10 | 2026-08-15 | issued
LSX-25-WNC-I-097-139 | 25-WNC-I-097 | SO4 | TB | Làm sạch, Sơn khung kiện (sơn 1 lớp) | TO-SON | m2 | 818.504 |  | 2025-11-10 | 2026-08-01 | issued
LSX-25-WNC-I-097-140 | 25-WNC-I-097 | DK1 | HR | Dạng Khung kiện | TO-TH | kg | 159008.5714 |  |  |  | issued
LSX-25-WNC-I-097-141 | 25-WNC-I-097 | DK2 | HR | Dạng Kiện gỗ | TO-TH | kg | 19614.7537 |  |  |  | issued
LSX-25-WNC-I-097-142 | 25-WNC-I-097 | GH2 | CO | Giao hàng Container (cho hàng vào container, lashing) | TO-TH | kg | 178623 |  | 2025-12-01 | 2026-09-15 | issued
LSX-25-SED-I-102-143 | 25-SED-I-102 | PC1 | TT | Pha Cắt tôn tấm khung kiện | TO-PC2 | kg | 2055.8979 |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-102-144 | 25-SED-I-102 | PC2 | TH | Pha Cắt thép hình khung kiện | TO-PC3 | kg | 10236.7047 |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-102-145 | 25-SED-I-102 | GC1 | SL | Gia công sấn khung kiện | TO-GCCK | kg |  |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-102-146 | 25-SED-I-102 | GC2 | CK | Gia công chính xác (tiện, phay, bào, ...) | TO-GCCK | kg |  |  |  |  | issued
LSX-25-SED-I-102-147 | 25-SED-I-102 | CT1 | KK | Đính gá khung kiện | TO-GL2 | kg | 1473 |  | 2025-11-15 | 2025-12-15 | issued
LSX-25-SED-I-102-148 | 25-SED-I-102 | CT2 | KK | Hàn khung kiện | TO-HAN1 | kg | 1473 |  | 2025-11-15 | 2025-12-15 | issued
LSX-25-SED-I-102-149 | 25-SED-I-102 | SO1 | TB | Làm sạch, Sơn sản phẩm (làm sạch SA2.5 sơn lớp 1) | TO-SON | m2 | 1190 |  | 2025-11-15 | 2025-12-15 | issued
LSX-25-SED-I-102-150 | 25-SED-I-102 | SO2 | TB | Sơn sản phẩm: Lớp 2 | TO-SON | m2 | 386 |  | 2025-11-15 | 2025-12-30 | issued
LSX-25-SED-I-102-151 | 25-SED-I-102 | SO3 | TB | Làm sạch, Sơn sản phẩm vật liệu hợp kim (ghi rõ số lớp sơn) | TO-SON | m2 |  |  |  |  | issued
LSX-25-SED-I-102-152 | 25-SED-I-102 | SO4 | TB | Làm sạch, Sơn khung kiện (sơn 1 lớp) | TO-SON | m2 | 66.864 |  | 2025-11-15 | 2025-12-15 | issued
LSX-25-SED-I-102-153 | 25-SED-I-102 | DK1 | KH | Dạng Khung kiện | TO-TH | kg | 11000 |  | 2025-12-01 | 2025-12-30 | issued
LSX-25-VPI-I-103-154 | 25-VPI-I-103 | PC1 | TT | Pha cắt tôn tấm | TO-PC2 | kg | 5166.85 |  | 2025-09-15 | 2025-10-05 | issued
LSX-25-VPI-I-103-155 | 25-VPI-I-103 | PC2 | TH | Pha cắt thép hình | TO-PC3 | kg | 14153.76 |  | 2025-09-15 | 2025-10-05 | issued
LSX-25-VPI-I-103-156 | 25-VPI-I-103 | GC2 | KH | Khoan lỗ | TO-GCCK | kg | 19320.6 |  | 2025-09-15 | 2025-10-25 | issued
LSX-25-VPI-I-103-157 | 25-VPI-I-103 | CT1 | KC | Đính Gá sản phẩm chính | TO-GL2 | kg | 18548.36 |  | 2025-10-01 | 2025-11-15 | issued
LSX-25-VPI-I-103-158 | 25-VPI-I-103 | CT | KC | Hàn sản phẩm chính | TO-HAN1 | kg | 18548.36 |  | 2025-10-01 | 2025-11-15 | issued
LSX-25-VPI-I-103-159 | 25-VPI-I-103 | CT4 | KK | Đính gá Khung kiện | TO-GL2 | kg | 772.25 |  | 2025-11-01 | 2025-11-20 | issued
LSX-25-VPI-I-103-160 | 25-VPI-I-103 | CT4 | KK | Hàn Khung kiện | TO-HAN1 | kg | 772.25 |  | 2025-11-02 | 2025-11-20 | issued
LSX-25-VPI-I-103-161 | 25-VPI-I-103 | CT5 |  | Tổ hợp sản phẩm |  | kg | 18548.36 |  | 2025-11-01 | 2025-11-15 | pending
LSX-25-VPI-I-103-162 | 25-VPI-I-103 | SO1 | TB | Làm sạch, Sơn sản phẩm (làm sạch SA2.5 sơn lớp 1) | TO-SON | m2 | 7.2 |  | 2025-11-15 | 2025-11-20 | issued
LSX-25-VPI-I-103-163 | 25-VPI-I-103 | DK1 | HR | Dạng Khung kiện | TO-GL2 | kg | 18548.36 |  | 2025-11-20 | 2025-11-27 | issued
LSX-25-VPI-I-103-164 | 25-VPI-I-103 | GH2 | CO | Giao hàng Container (cho hàng vào container, lashing) | TO-GL2 | kg | 18548.36 |  | 2025-12-05 | 2025-12-05 | issued
LSX-25-WNC-I-104-165 | 25-WNC-I-104 | PC1 | TT | Pha cắt tôn tấm MLI- 1617 | TO-PC2 | kg | 846 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-166 | 25-WNC-I-104 | PC2 | TT | Pha cắt tôn tấm MLI- 1634 | TO-PC2 | kg | 22845 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-167 | 25-WNC-I-104 | PC3 | TT | Pha cắt tôn tấm MLI- 1645 | TO-PC2 | kg | 1052 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-168 | 25-WNC-I-104 | PC4 | TT | Pha cắt tôn tấm MLI- 1652 | TO-PC2 | kg | 263 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-169 | 25-WNC-I-104 | PC5 | TH | Pha cắt thép hình MLI- 1617 | TO-PC3 | kg | 846 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-170 | 25-WNC-I-104 | PC6 | TH | Pha cắt thép hình MLI- 1645 | TO-PC3 | kg | 115 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-171 | 25-WNC-I-104 | PC7 | TH | Pha cắt thép hình MLI- 1652 | TO-PC3 | kg | 1203 |  | 2026-04-01 | 2026-06-16 | issued
LSX-25-WNC-I-104-172 | 25-WNC-I-104 | PC8 | TT | Pha cắt tôn tấm khung kiện | TO-PC2 | kg |  |  | 2026-05-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-173 | 25-WNC-I-104 | PC9 | TH | Pha Cắt thép hình khung kiện | TO-PC3 | kg |  |  | 2026-05-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-174 | 25-WNC-I-104 | GC1 | SL | Gia công sấn, lốc MLI- 1617 | TO-GCCK | kg | 1692 |  | 2026-06-06 | 2026-06-16 | issued
LSX-25-WNC-I-104-175 | 25-WNC-I-104 | GC2 | SL | Gia công sấn, lốc MLI- 1634 | TO-GCCK | kg | 22539 |  | 2026-04-07 | 2026-04-20 | issued
LSX-25-WNC-I-104-176 | 25-WNC-I-104 | GC3 | KH | Khoan lỗ MLI- 1634 | TO-GCCK | kg | 22539 |  | 2026-04-07 | 2026-05-29 | issued
LSX-25-WNC-I-104-177 | 25-WNC-I-104 | GC4 | CK | Gia công chính xác (tiện, phay, bào, ...) | TO-GCCK | kg |  |  |  |  | issued
LSX-25-WNC-I-104-178 | 25-WNC-I-104 | CT1 | TB | Steel frame MLI- 1617 | TO-GL2 | kg | 1009 |  | 2026-04-10 | 2026-05-10 | issued
LSX-25-WNC-I-104-179 | 25-WNC-I-104 | CT2 | TB | panels (outer sheet 4mm and stiffeners), outer sheet welded through MLI- 1617 | TO-GL2 | kg | 198 |  | 2026-04-10 | 2026-05-10 | issued
LSX-25-WNC-I-104-180 | 25-WNC-I-104 | CT3 | TB | Steel construction Walkway/Duct MLI- 1617 | TO-GL2 | kg | 98 |  | 2026-04-10 | 2026-05-10 | issued
LSX-25-WNC-I-104-181 | 25-WNC-I-104 | CT4 | TB | Handrail & Ladder Walkway MLI- 1617 | TO-GL2 | kg | 114 |  | 2026-04-10 | 2026-05-10 | issued
LSX-25-WNC-I-104-182 | 25-WNC-I-104 | CT5 | TB | Flashing Kit; painted (S.N 8.2) MLI- 1617 | TO-GL2 | kg | 273 |  | 2026-04-10 | 2026-05-10 | issued
LSX-25-WNC-I-104-183 | 25-WNC-I-104 | CT6 | TB | Steel frame MLI- 1617 | TO-HAN1 | kg | 1009 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-184 | 25-WNC-I-104 | CT7 | TB | panels (outer sheet 4mm and stiffeners), outer sheet welded through MLI- 1617 | TO-HAN1 | kg | 198 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-185 | 25-WNC-I-104 | CT8 | TB | Steel construction Walkway/Duct MLI- 1617 | TO-HAN1 | kg | 98 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-186 | 25-WNC-I-104 | CT9 | TB | Handrail & Ladder Walkway MLI- 1617 | TO-HAN1 | kg | 114 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-187 | 25-WNC-I-104 | CT10 | TB | Flashing Kit; painted (S.N 8.2) MLI- 1617 | TO-HAN1 | kg | 273 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-WNC-I-104-188 | 25-WNC-I-104 | CT12 | TB | Steel frame acc. to drawings; HDG or painted (S.N 1.2) sheet welded through + panels (outer sheet 4m | TO-GL1 | kg | 7586.4926 |  | 2026-04-19 | 2026-05-29 | issued
LSX-25-WNC-I-104-189 | 25-WNC-I-104 | CT13 | TB | Steel frame acc. to drawings; HDG or painted (S.N 1.2) sheet welded through + panels (outer sheet 4m | TO-GL3 | kg | 9130.1982 |  | 2026-04-19 | 2026-05-29 | issued
LSX-25-WNC-I-104-190 | 25-WNC-I-104 | CT14 | TB | Steel frame acc. to drawings; HDG or painted (S.N 1.2) sheet welded through + panels (outer sheet 4m | TO-GL4 | kg | 6128.3093 |  | 2026-04-19 | 2026-05-29 | issued
LSX-25-WNC-I-104-191 | 25-WNC-I-104 | CT15 | TB | Steel frame acc. to drawings; HDG or painted (S.N 1.2) sheet welded through + panels (outer sheet 4m | TO-HAN1 | kg | 9130.1982 |  | 2026-04-19 | 2026-05-29 | issued
LSX-25-WNC-I-104-192 | 25-WNC-I-104 | CT16 | TB | Steel frame acc. to drawings; HDG or painted (S.N 1.2) sheet welded through + panels (outer sheet 4m | TO-HAN2 | kg | 13714.8018 |  | 2026-04-19 | 2026-05-29 | issued
LSX-25-WNC-I-104-193 | 25-WNC-I-104 | CT17 | TB | KCT MLI- 1645 |  | kg | 1052 |  | 2026-05-16 | 2026-06-05 | pending
LSX-25-WNC-I-104-194 | 25-WNC-I-104 | CT18 | TB | Kết cấu sàn, lan can, cầu thang MLI- 1645 |  | kg | 115 |  | 2026-05-16 | 2026-06-05 | pending
LSX-25-WNC-I-104-195 | 25-WNC-I-104 | CT19 | TB | Sản phẩm chính MLI- 1652 |  | kg | 1466 |  |  |  | pending
LSX-25-WNC-I-104-196 | 25-WNC-I-104 | CT20 | TB | KCT MLI- 1645 |  | kg | 1052 |  | 2026-05-16 | 2026-06-05 | pending
LSX-25-WNC-I-104-197 | 25-WNC-I-104 | CT21 | TB | Kết cấu sàn, lan can, cầu thang MLI- 1645 |  | kg | 115 |  | 2026-05-16 | 2026-06-05 | pending
LSX-25-WNC-I-104-198 | 25-WNC-I-104 | CT22 | TB | Sản phẩm chính MLI- 1652 |  | kg | 1466 |  |  |  | pending
LSX-25-WNC-I-104-199 | 25-WNC-I-104 | CT23 | KK | KCT (Skid of Packing) |  | kg | 30369 |  | 2026-05-15 | 2026-06-05 | pending
LSX-25-WNC-I-104-200 | 25-WNC-I-104 | CT24 | KK | KCT (Skid of Packing) |  | kg | 30369 |  | 2026-05-15 | 2026-06-05 | pending
LSX-25-WNC-I-104-201 | 25-WNC-I-104 | VH2 | TB | Tổ hợp sản phẩm (MLI-1634) Unit 1 | TO-GL3 | kg | 22845 |  | 2026-06-05 | 2026-06-15 | issued
LSX-25-WNC-I-104-202 | 25-WNC-I-104 | VH5 | TB | Tổ hợp sản phẩm (MLI-1652) Unit 1 |  | kg | 1553 |  | 2026-06-25 | 2026-07-05 | pending
LSX-25-WNC-I-104-203 | 25-WNC-I-104 | SO1 | TB | Grit blasting Sa 2 ½ or SSPC SP10 Primer Interzinc 52 or 22 Organic or Inorganic Zinc 50µm Grey or G | TO-SON | m2 | 53.1616 |  | 2026-05-15 | 2026-06-05 | issued
LSX-25-WNC-I-104-204 | 25-WNC-I-104 | SO2 | TB | Interguard 475HS 120 micron MLI-1617 | TO-SON | m2 | 30.0351 |  | 2026-05-15 | 2026-06-05 | issued
LSX-25-WNC-I-104-205 | 25-WNC-I-104 | SO3 | TB | Interthane 990 50 micron MLI-1617 | TO-SON | m2 | 30.0351 |  | 2026-05-15 | 2026-06-05 | issued
LSX-25-WNC-I-104-206 | 25-WNC-I-104 | SO4 | TB | Grit blasting Sa 2 ½ or SSPC SP10 Primer Interzinc 52 or 22 Organic or Inorganic Zinc 50µm Grey or G | TO-SON | m2 | 907.4687 |  | 2026-06-05 | 2026-07-05 | issued
LSX-25-WNC-I-104-207 | 25-WNC-I-104 | SO5 | TB | Intermediate Intergard 475HS or 345 Epoxy 120µm Buff or White MLI-1634 | TO-SON | m2 | 547.6059 |  | 2026-06-05 | 2026-07-05 | issued
LSX-25-WNC-I-104-208 | 25-WNC-I-104 | SO6 | TB | Finish Interthane 990 Polyuretanic 50µm RAL 7035 MLI-1634 | TO-SON | m2 | 547.6059 |  | 2026-06-05 | 2026-07-05 | issued
LSX-25-WNC-I-104-209 | 25-WNC-I-104 | SO7 | TB | Làm sạch, Sơn sản phẩm (ghi rõ số lớp sơn) MLI-1645 | TO-SON | m2 | 21.4624 |  | 2026-06-05 | 2026-06-20 | issued
LSX-25-WNC-I-104-210 | 25-WNC-I-104 | SO8 | TB | Làm sạch, Sơn sản phẩm (ghi rõ số lớp sơn) MLI-1652 | TO-SON | m2 | 42.9249 |  | 2026-06-05 | 2026-06-05 | issued
LSX-25-WNC-I-104-211 | 25-WNC-I-104 | SO9 | KK | Làm sạch, Sơn khung kiện (ghi rõ số lớp sơn) MLI-1617 | TO-SON | m2 |  |  | 2026-06-15 | 2026-08-10 | issued
LSX-25-WNC-I-104-212 | 25-WNC-I-104 | SO10 | KK | Làm sạch, Sơn khung kiện (ghi rõ số lớp sơn) MLI-1634 | TO-SON | m2 |  |  | 2026-06-15 | 2026-08-10 | issued
LSX-25-WNC-I-104-213 | 25-WNC-I-104 | SO12 | KK | Làm sạch, Sơn khung kiện (ghi rõ số lớp sơn) MLI-1652 | TO-SON | m2 |  |  | 2026-06-15 | 2026-08-10 | issued
LSX-25-WNC-I-104-214 | 25-WNC-I-104 | DK1 | HR | Đóng kiện MLI-1617 | TO-TH | kg | 1924 |  | 2026-06-05 | 2026-06-15 | issued
LSX-25-WNC-I-104-215 | 25-WNC-I-104 | DK2 | HR | Đóng kiện MLI-1634 | TO-TH | kg | 24934 |  | 2026-07-10 | 2026-07-25 | issued
LSX-25-WNC-I-104-216 | 25-WNC-I-104 | DK3 | HR | Dạng Khung kiện MLI-1645 | TO-TH | kg | 1958 |  | 2026-06-20 | 2026-06-30 | issued
LSX-25-WNC-I-104-217 | 25-WNC-I-104 | DK4 | HR | Đóng kiện MLI-1652 | TO-TH | kg | 1553 |  | 2026-07-05 | 2026-07-15 | issued
LSX-25-WNC-I-104-218 | 25-WNC-I-104 | DK5 | HR | ĐÓNG Kiện các sản phẩm khách hàng gửi | TO-TH | kg |  |  |  |  | issued
LSX-25-WNC-I-104-219 | 25-WNC-I-104 | GH1 | PT | Giao lên phương tiện vận chuyển MLI-1617 | TO-TH | kg | 1793.4369 |  | 2026-09-14 | 2026-09-14 | issued
LSX-25-WNC-I-104-220 | 25-WNC-I-104 | GH2 | PT | Giao lên phương tiện vận chuyển MLI-1634 | TO-TH | kg | 24448.9348 |  | 2026-09-14 | 2026-09-14 | issued
LSX-25-WNC-I-104-221 | 25-WNC-I-104 | GH3 | PT | Giao lên phương tiện vận chuyển MLI-1645 | TO-TH | kg | 1468.3534 |  | 2026-09-14 | 2026-09-14 | issued
LSX-25-WNC-I-104-222 | 25-WNC-I-104 | GH4 | PT | Giao lên phương tiện vận chuyển MLI-1652 | TO-TH | kg | 1781.5682 |  | 2026-09-14 | 2026-09-14 | issued
LSX-25-WNC-I-104-223 | 25-WNC-I-104 | GH5 | CO | Giao hàng Container (cho hàng vào container, lashing) | TO-TH | kg |  |  |  |  | issued
LSX-25-SED-I-105-224 | 25-SED-I-105 | PC1 | TT | Pha Cắt tôn tấm khung kiện | TO-PC2 | kg | 76.0062 |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-105-225 | 25-SED-I-105 | PC2 | TH | Pha Cắt thép hình khung kiện | TO-PC3 | kg | 1720 |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-105-226 | 25-SED-I-105 | GC1 | SL | Gia công sấn khung kiện | TO-GCCK | kg | 1796 |  | 2025-11-10 | 2025-11-20 | issued
LSX-25-SED-I-105-227 | 25-SED-I-105 | SO1 | TB | Làm sạch, Sơn sản phẩm (làm sạch SA2.5 sơn lớp 1) | TO-SON | m2 |  |  |  |  | issued
LSX-25-SED-I-105-228 | 25-SED-I-105 | SO2 | TB | Sơn sản phẩm: Lớp 2 | TO-SON | m2 |  |  |  |  | issued
LSX-25-SED-I-105-229 | 25-SED-I-105 | SO3 | TB | Làm sạch, Sơn sản phẩm vật liệu hợp kim (ghi rõ số lớp sơn) | TO-SON | m2 |  |  |  |  | issued
LSX-25-SED-I-105-230 | 25-SED-I-105 | SO4 | TB | Làm sạch, Sơn khung kiện (sơn 1 lớp) | TO-SON | m2 |  |  |  |  | issued
LSX-25-SED-I-105-231 | 25-SED-I-105 | DK1 | KH | Dạng Khung kiện | TO-TH | kg |  |  |  |  | issued
LSX-25-GON-I-106-232 | 25-GON-I-106 | PC1 | TT | Pha cắt tôn tấm | TO-PC2 | kg | 59.9268 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-233 | 25-GON-I-106 | PC2 | TH | Pha cắt thép hình | TO-PC3 | kg | 228.9749 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-234 | 25-GON-I-106 | PC3 | IN | Pha cắt Inox, hợp kim | TO-PC2 | kg | 32.1172 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-235 | 25-GON-I-106 | PC4 | IN | Pha cắt Inox, hợp kim | TO-PC3 | kg | 3.4343 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-236 | 25-GON-I-106 | PC4 | TT | Pha cắt biện pháp | TO-PC2 | kg | 20 |  | 2026-01-11 | 2026-01-23 | issued
LSX-25-GON-I-106-237 | 25-GON-I-106 | GC1 | SL | Gia công sấn, lốc | TO-GCCK | kg | 28.54 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-238 | 25-GON-I-106 | GC2 | KH | Khoan lỗ | TO-GCCK | kg | 151.1436 |  | 2025-11-11 | 2025-11-18 | issued
LSX-25-GON-I-106-239 | 25-GON-I-106 | GC3 | CK | Gia công chính xác (tiện, phay, bào, ...) | TO-GCCK | kg |  |  | 2025-12-04 | 2025-12-30 | issued
LSX-25-GON-I-106-240 | 25-GON-I-106 | CT1 | TB | Sản phẩm chính | TO-GL2 | kg | 554 |  | 2025-12-02 | 2026-01-23 | issued
LSX-25-GON-I-106-241 | 25-GON-I-106 | CT1 | TB | Sản phẩm chính | TO-HAN1 | kg | 554 |  | 2025-12-02 | 2026-01-23 | issued
LSX-25-GON-I-106-242 | 25-GON-I-106 | CT1 | TB | Tổ hợp sản phẩm | TO-GL2 | kg | 554 |  | 2026-01-05 | 2026-01-07 | issued
LSX-25-GON-I-106-243 | 25-GON-I-106 | CN1 | TB | Tổ hợp sản phẩm (sau sơn, hoặc sau bảo ôn) | TO-GL2 | bộ | 1 |  | 2026-01-31 | 2026-01-31 | issued
LSX-25-GON-I-106-244 | 25-GON-I-106 | SO1 | TB | Làm sạch |  | m2 | 8 |  | 2026-01-24 | 2026-01-25 | pending
LSX-25-GON-I-106-245 | 25-GON-I-106 | SO1 | TB | Sơn sản phẩm (Sơn 03 lớp) |  | m2 | 8 |  | 2026-01-26 | 2026-01-30 | pending
LSX-25-GON-I-106-246 | 25-GON-I-106 | DK2 | HR | Dạng Kiện gỗ |  | kg | 554 |  | 2026-01-30 | 2026-01-30 | pending
LSX-25-GON-I-106-247 | 25-GON-I-106 | GH1 | PT | Giao lên phương tiện vận chuyển |  | kg | 554 |  | 2026-03-01 | 2026-03-01 | pending
LSX-26-LS5-O-107-248 | 26-LS5-O-107 | LS+S - TB/BL | TB | Làm sạch, Sơn sản phẩm (sơn 1 lớp) | TO-SON | m2 | 300 |  |  |  | issued
LSX-25-GEN-G-07-249 | 25-GEN-G-07 | TT | TT | Pha cắt tôn tấm | TO-PC2 | kg | 23437 |  | 2026-01-23 | 2026-01-26 | issued
LSX-25-GEN-G-07-250 | 25-GEN-G-07 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 4586 |  | 2026-01-23 | 2026-01-26 | issued
LSX-25-GEN-G-07-251 | 25-GEN-G-07 | SL | SL | Gia công sấn, lốc | TO-GCCK | kg |  |  |  |  | issued
LSX-25-GEN-G-07-252 | 25-GEN-G-07 | KH | KH | Khoan lỗ | TO-GCCK | kg | 28023 |  | 2026-01-26 | 2026-02-05 | issued
LSX-25-GEN-G-07-253 | 25-GEN-G-07 | KC | KC | Chế tạo khung sàn máy | TO-PC3 | kg | 28023 |  | 2026-01-28 | 2026-02-19 | issued
LSX-25-GEN-G-07-254 | 25-GEN-G-07 | KC | KC | Chế tạo khung sàn máy | TO-HAN2 | kg | 28023 |  | 2026-01-31 | 2026-02-25 | issued
LSX-25-GEN-G-07-255 | 25-GEN-G-07 | TH | KC | Tổ hợp khung sàn máy lazer | TO-PC2 | kg | 28023 |  | 2026-02-26 | 2026-03-07 | issued
LSX-25-GEN-G-07-256 | 25-GEN-G-07 | CN | CN | Chạy thử+học vạn hành máy | TO-PC2 | Công |  |  | 2026-03-09 | 2026-03-14 | issued
LSX-25-GEN-G-07-257 | 25-GEN-G-07 | LS | TB | Làm sạch | TO-SON | m2 | 300 |  | 2026-02-25 | 2026-02-26 | issued
LSX-25-GEN-G-07-258 | 25-GEN-G-07 | S | TB | Sơn | TO-SON | m2 | 300 |  | 2026-02-26 | 2026-02-27 | issued
LSX-25-GEN-G-08-259 | 25-GEN-G-08 | PC1 | TT | Pha cắt tôn tấm | TO-PC2 | kg | 4203.6 |  | 2026-04-01 | 2026-05-15 | issued
LSX-25-GEN-G-08-260 | 25-GEN-G-08 | PC2 | TH | Pha cắt thép hình | TO-PC3 | kg | 246.6 |  | 2026-04-01 | 2026-05-15 | issued
LSX-25-GEN-G-08-261 | 25-GEN-G-08 | GC1 | SL | Gia công sấn, lốc | TO-GCCK | kg | 4203.6 |  | 2026-04-01 | 2026-05-15 | issued
LSX-25-GEN-G-08-262 | 25-GEN-G-08 | CT1 | TB | Palet đựng bôi | TO-PC3 | kg | 4450 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-GEN-G-08-263 | 25-GEN-G-08 | CT1 | TB | Palet đựng bôi | TO-HAN2 | kg | 4450 |  | 2026-04-10 | 2026-05-15 | issued
LSX-25-GEN-G-08-264 | 25-GEN-G-08 | SO1 | TB | Sơn 1 nước | TO-SON | m2 |  |  |  |  | issued
LSX-25-GEN-G-09-265 | 25-GEN-G-09 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 23.6 |  | 2026-01-07 | 2026-01-07 | issued
LSX-25-GEN-G-09-266 | 25-GEN-G-09 | KC | KC | Chế tạo cột Camera Cây Hương | TO-PC3 | kg | 23.6 |  | 2026-01-07 | 2026-01-07 | issued
LSX-25-GEN-G-09-267 | 25-GEN-G-09 | LD | LT | Lắp cột Camera Cây Hương | TO-PC3 | kg | 23.6 |  | 2026-01-07 | 2026-01-07 | issued
LSX-26-GEN-G-10-268 | 26-GEN-G-10 | TT | TT | Pha cắt tôn tấm | TO-PC2 | kg | 188.1 |  | Chưa có thông tin từ DA |  | issued
LSX-26-GEN-G-10-269 | 26-GEN-G-10 | TH | TH | Pha cắt thép hình | TO-PC3 | kg | 61165 |  | Chưa có thông tin từ DA |  | issued
LSX-26-GEN-G-10-270 | 26-GEN-G-10 | SL | SL | Gia công sấn, lốc | TO-GCCK | kg |  |  |  |  | issued
LSX-26-GEN-G-10-271 | 26-GEN-G-10 | KH | KH | Khoan lỗ | TO-GCCK | kg | 61353.1 |  | Chưa có thông tin từ DA |  | issued
LSX-26-GEN-G-10-272 | 26-GEN-G-10 | PS | PS | Nhân công dọn mặt bằng | TO-PC3 | Công |  |  |  |  | issued

## HƯỚNG DẪN
Hướng dẫn điền dữ liệu
Tên cột | Cột DB | Bắt buộc | Ghi chú
Mã lệnh SX | lenh_sx_code | ✅ | Mã duy nhất
Mã dự án | project_code | ✅ | FK → project_master
Mã công việc | job_code | ✅ | FK → job_code_master
Phân loại phụ | sub_item
Nội dung | noi_dung
Mã tổ SX | team_code | ✅ | FK → to_san_xuat.team_code
ĐVT | don_vi_tinh
KL phân giao | kl_phan_giao | ✅ | kg
Đơn giá khoán | don_gia |  | VND/kg
Ngày bắt đầu | ngay_bat_dau |  | YYYY-MM-DD
Ngày kết thúc | ngay_ket_thuc |  | YYYY-MM-DD
Trạng thái | trang_thai |  | draft/issued/in_progress/done